## Slide 1: NCIP Nanomaterial Data Curation Initiative Update & path forward Christine Ogilvie Hendren 5/29/2014

## Slide 2: Nano Data Curation Initiative
Scope of project
Timeline
Next steps

## Slide 3: Nano Data Curation Initiative
Scope of project
Timeline
Next steps

## Slide 4: Curation Sub-Topics
Nano Data Curation Initiative Framing Paper
Sub-topics:
Curation Workflows
Data completeness
Data quality
Curator responsibilities
Primary key definition
Temporal metadata: Instance of characterization
Protocol developments
Integration between databases and datasets
Sourcing data

## Slide 5: Curation Sub-Topics
Nano Data Curation Initiative Framing Paper
Sub-topics:
Curation Workflows (include protocols, curator responsibilities?)
Data completeness (include data quality?)
Data quality
Curator responsibilities
Primary key definition
Temporal metadata: Instance of characterization
Protocol developments
Integration between databases and datasets
Sourcing data

## Slide 6: Curation Sub-Topics
Nano Data Curation Initiative Framing Paper
Sub-topics:
Curation Workflows (include protocols, curator responsibilities?)
Data completeness (include data quality?)
Primary key definition
Temporal metadata: Instance of characterization
Integration between databases and datasets
Sourcing data

## Slide 8: Nano Data Curation Initiative
Scope of project
Timeline
Next steps

## Slide 9: Timeline (not to scale)
Nanomaterial Data Curation Initiative (NDCI) Framing Paper – 1st Draft shared with authors
Call for content across all sub-topics – identified workflow as a good starting point
Sub-topic 1: Curation Workflow consensus paper initial NanoWG working session during call
Initial stakeholder inquiry: general invitation to contribute
NDCI interest group meeting
Framing paper:
Author input deadline
Sub-topic 1: Curation Workflow Team ID’ed
1
2
3
4
5
6
7
Jan 9 2014
Mar 20 2014
May 15, 2014
Feb 5 2014
Feb 24 2014
Apr 15 2014
June 12, 2014

## Slide 10: Timeline (not to scale)
Curation Workflow questions shared with stakeholders
Curation Framing Paper Submitted (after finalization/clearance)
Curation Workflow Paper Submitted (after finalization/clearance)
Framing Paper: Final draft distributed to authors for review
Sub-topic 2: Data completeness initial NanoWG working session during call
Data completeness questions shared with stakeholders
8
9
10
June 15 2014
July 31 2014
Aug 15, 2014
Ongoing
Jun 19 2014
Jul 24 2014
Oct 24, 2014
12
Curation Workflow 1st Draft Shared with authors
Sub-topic 2: Data completeness Team ID’ed
11
Jun 30 2014
Aug 4 2014
13
15
14

## Slide 11: Nano Data Curation Initiative
Scope of project
Timeline
Next steps

## Slide 12: Next Steps
Review writing process on HUB
Review outline of papers on HUB
Identify author teams
Discuss consolidation and agree on final sub-topic list

## Slide 13
Questions?